## Instructions
Manpower & Quantity Loading Template — How To Use
1. Go to the 'Input' tab. Paste (or type) your data starting in row 2, columns A-H, matching the
header row exactly: Commodity ¦ Baseline Qty ¦ Baseline Hours ¦ Unit Rate (Hrs/Qty) ¦
Direct or Indirect ¦ WHC or SUB ¦ Start Date ¦ Finish Date. That's the only thing you paste.
2. Columns I-P calculate automatically the moment you fill in a row (real Excel formulas — no
macro needed): Duration (Days/Weeks), Hrs/Day, Hrs/Week, FTE, Qty/Day, Qty/Week, and
Avg Qty/Day/Person. FTE is based on the 'Hours per FTE per Week' assumption in cell S1
(default 60) — change that one cell to change the FTE basis for every row at once.
3. The 'Calendar' tab spreads every row's Baseline Hours and Baseline Qty in a straight line
across its Start->Finish window, into weekly buckets running left to right, with Total Hours,
Total FTE, and Total Qty per week at the bottom. That tab is generated for you — after you
paste new or changed rows on Input, just ask Claude Code to refresh the Calendar tab (or run
scripts/generate_calendar.py) and it rebuilds the whole grid to match your new date range.
4. The template ships with 25 commodity rows. If you need more, select row 26 and copy it down —
every Input formula is relative to its own row so it extends cleanly.
Color key: Yellow fill / blue text = cells you edit. Black text = formulas — do not overwrite.

## Input
Commodity | Baseline Qty | Baseline Hours | Unit Rate (Hrs/Qty) | Direct or Indirect | WHC or SUB | Start Date | Finish Date | Duration (Days) | Duration (Weeks) | Hrs/Day | Hrs/Week | FTE (60 hrs/wk) | Qty/Day | Qty/Week | Avg Qty/Day/Person | Assumption: Hours per FTE per Week | 60
Structural Steel Erection | 1250 | 18750 | 15 | Direct | WHC | 2026-01-05 | 2026-04-27
Note on A2: Example row - overwrite or delete before entering real data.

## Calendar
Weekly Manpower & Quantity Calendar
Straight-line spread of each Input row's Baseline Hours / Baseline Qty across its Start-Finish window, in weekly buckets left to right. Regenerated by scripts/generate_calendar.py — re-run after editing the Input tab.
Commodity | WHC or SUB | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
HOURS PER WEEK (Baseline Hours spread straight-line across Start-Finish)
Commodity | WHC or SUB | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
Structural Steel Erection | WHC | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 165.93
TOTAL HOURS / WEEK |  | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 1161.5 | 165.93
TOTAL FTE (Hrs/Week / FTE basis) |  | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 19.36 | 2.77
QUANTITY PER WEEK (Baseline Qty spread straight-line across Start-Finish)
Commodity | WHC or SUB | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
Structural Steel Erection | WHC | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 11.06
TOTAL QTY / WEEK |  | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 77.43 | 11.06